## Sheet1
Studio Name |  | Downstream
| Asset Name | Notes (Asset Purpose) | Due Date | Completed | Implemented
Scripts/Mechs | Follow Camera System | Camera follows the player | Nov 12th 2025 | Completed | Implemeneted
| PlayerController | The script controlling the player | Nov 12th 2025 | Completed | Implemented
| Movement | Forward, back, right, and left movement | Nov 12th 2025 | Completed | Implemented
| Crouch | A way to hide from enemies | Nov 18th 2025 | Completed | Implemented
| Running | A faster movement option | Nov 18th 2025 | Completed | Implemented
| Item Pick Up | A way to pick up items | Nov 18th 2025 | Completed | Implemented
| Item Toss | A throwing system so that you can stun enemies | Nov 18th 2025 | Completed | Implemented
| Game Over System | After the player dies the game restarts after the last check point | Nov 13th 2025 | Completed | Implemented
| Pause Menu | A pause menu which appears after pressing escape, stoping the game and giving options to resume, quit, or go to the main menu | Nov 13th 2025 | Completed | Implemented
| Main Menu | The menu which starts the game or allows you to quit the game | Nov 13th 2025 | Completed | Implemented
| Quit | Exits the game | Nov 13th 2025 | Completed | Implemented
| Check Point | After death the player respawns at the last check point the player hit | Nov 19th 2025 | Completed | Implemented
| Enemy Stun System | If an enemy gets hit by an item thrown by the player, the enemy will be stunned | Nov 18th 2025 | Completed | Implemented
| Enemy Movement System | The way an enemy moves | Nov 12th 2025 | Completed | Implemented
| Boss Movement System | The way the boss enemy moves | Dec 3rd 2025 | Scrapped
| UI System | Visible indications of health, damage, pause menu, player stats, and buttons | Nov 24th 2025 | Completed | Implemented
| Button Mashing Mechanic | A way to get the player unstuck from puzzles | Nov 26th 2025 | Completed | Implemented
| Inventory | A way to show the items the player has collected | Nov 12th 2025 | Completed | Implemented
| Enemy Detection System | A way to allow enemies to follow and detect the player | Nov 12th 2025 | Completed | Implemented
Levels | Distraction Puzzles | Toss an Item to distract enemies and lead them away from the player | Nov 20th 2025 | Completed | Implemented
| Stun Puzzles | Toss an Item at an enemy to freeze them momentarily | Nov 21st 2025 | Completed | Implemented
| Stealth Puzzles | Sneak around enemies and hide behind objects | Nov 21st 2025 | Completed | Implemented
| Collectible Areas Level 1 | Where Collectibles will reside within levels | Nov 19th 2025 | Scrapped
| Collectible Areas Level 2 | Where Collectibles will reside within levels | Nov 24th 2025 | Scrapped
| Collectible Areas Level 3 | Where Collectibles will reside within levels | Dec 1st 2025 | Scrapped
| Lure Puzzle | Use an item or run past an enemy to lure them away | Nov 28th 2025 | Completed | Implemented
| Sink Hole Puzzles | Avoid broken tiles in the floor to avoid getting stuck | Nov 27th 2025 | Completed | Implemented
| Pressure Plate Puzzles | Avoid sound tiles on the floor to avoid alerting enemies | Nov 28th 2025 | Scrapped
| Boss Fight | The boss fight at the end of the game | Dec 11th 2025 | Scrapped
| Key Puzzles | Find keys to unlock passageways and doors | Dec 4th 2025 | Completed | Implemented
Music/SFX | Menu Music | Background Music for Menu | Nov 13th 2025 | Completed | Implemented
| Beginning Cutscene Music | Music to accompany the Cutscene | Nov 24th 2025 | Scrapped
| Ending Cutscene Music | Music to accompany the Cutscene | Dec 5th 2025 | Scrapped
| Level 1 Music | Music to play in the background of the level | Nov 18th 2025 | Completed | Implemented
| Level 2 Music | Music to play in the background of the level | Nov 28th 2025 | Completed | Implemented
| Level 3 Music | Music to play in the background of the level | Dec 5th 2025 | Completed | Implemented
| Boss Fight Music | Music to play during the Boss Fight | Dec 4th 2025 | Scrapped
| Check Point SFX | Noise to alert the player of a checkpoint | Nov 19th 2025 | Completed | Implemented
| Guard Enemy SFX | Noises made by the Guard Enemy | Nov 18th 2025 | Completed | Implemented
| Chase Enemy SFX | Noises made by the Chase Enemy | Dec 4th 2025 | Completed | Implemented
| Camera Enemy SFX | Noises made by the Camera Enemy | Dec 5th 2025 | Completed | Implemented
| Boss SFX | Noises made by the Boss Enemy | Dec 5th 2025 | Scrapped
| Player Death SFX | Sound played when the Player dies | Nov 18th 2025 | Completed | Implemented
| Player Movement SFX | Sound played when the Player moves across the tilemap | Nov 24th 2025 | Scrapped
| Item SFX | Different Noises for picking up, dropping, throwing an item | Nov 19th 2025 | Completed | Implemented
| Collectible SFX | Noises when a collectible is near or obtained | Nov 28th 2025 | Scrapped
| Guide SFX | Noises made by the guide character | Dec 1st 2025 | Scrapped
| Dialogue SFX | Sound effects made during dialogue | Dec 5th 2025 | Scrapped
| POSSIBLE VOICE ACTING | Possible voice acting for the guide character | Dec 16th 2025 | Scrapped
| Beginning Dialogue | Dialogue during cutscenes to give more context to the story | Nov 18th 2025 | Scrapped
| Level 1 Dialogue | Dialogue throughout level 1 | Nov 28th 2025 | Scrapped
| Level 2 Dialogue | Dialogue throughout level 2 | Dec 4th 2025 | Scrapped
| Level 3 Dialogue | Dialouge throughout level 3 | Dec 5th 2025 | Scrapped
| Ending 1 Dialogue | Dialogue for the 1st ending | Dec 5th 2025 | Scrapped
| Ending 2 Dialogue | Dialogue for the 2nd ending | Dec 5th 2025 | Scrapped
| Pressure Plate SFX | Noise made by pressure plate when activated | Nov 28th 2025 | Scrapped
| Alert SFX | Noise made to let the player know when an enemy has been alerted to their supposed location | Nov 28th 2025 | Completed | Implemented
Art/Animation | Player Sprite | The character art for the player | Nov 14th 2025 |  | Implemented
| Player Movement Animation | The movement animation for the player when they move forward, backward, right, and left | Nov 14th 2025 |  | Implemented
| Player Special Animations | Player animations like crouch or throw | Nov 14th 2025 |  | Implemented
| Guide Character Sprite | The art for the guide character | Nov 14th 2025 | Scrapped
| Guide Movement Animations | The animation for when the guide character moves forward, backward, right, and left | Nov 14th 2025 | Scrapped
| Player Text Portrait | The art that will appear alonside textboxes to convey emotion and indicate who is speaking | Nov 14th 2025 | Scrapped
| Guide Text Portrait | The art that will appear alonside textboxes to convey emotion and indicate who is speaking | Nov 14th 2025 | Scrapped
| Guard Enemy Sprite | The art for the guard enemy | Nov 19th 2025 |  | Implemented
| Guard Enemy Movement Animations | The animation for when the guard enemy moves forward, backward, right, and left | Nov 19th 2025 |  | Implemented
| Guard Enemy Attack Animations | The animation for when the guard enemy attacks the player | Nov 19th 2025 |  | Implemented
| Chase Enemy Sprite | The art for the chase enemy | Nov 25th 2025 |  | Implemented
| Chase Enemy Movement Animations | The animation for when the chase enemy moves forward, backward, left, and right | Nov 25th 2025 |  | Implemented
| Chase Enemy Attack Animations | The animation for when the chase enemy attacks the player | Nov 25th 2025 |  | Implemented
| Camera Enemy Sprites | The character art for the camera enemy | Nov 28th 2025 |  | Implemented
| Camera Enemy Movement Animations | The animations for the camera enemy when it moves. | Nov 28th 2025 |  | Implemented
| Camera Enemy Attack Animations | The animation for when the camera enemy attacks the player | Nov 28th 2025 |  | Implemented
| Check Point Sprites | The art for the checkpoints so the player knows where they are | Dec 11th 2025 |  | Implemented
| Main Menu Art | The art for the main menu, and art for the main menu buttons | Nov 19th 2025 | Completed | Implemented
| Sand Texture | Environmental art for the sand | Dec 8th 2025 |  | Implemented
| Water Texture | Environmental art for the water | Dec 8th 2025 |  | Implemented
| Level 1 Floor Texture | Floor texture for level 1 | Dec 8th 2025 |  | Implemented
| Level 1 Wall Texture | Wall texture for level 1 | Dec 8th 2025 |  | Implemented
| Level 2 Floor Texture | Floor texture for level 2 | Dec 8th 2025 |  | Implemented
| Level 2 Wall Texture | Wall texture for level 2 | Dec 8th 2025 |  | Implemented
| Rock Sprite | The sprite for the rock the player can throw | Nov 14th 2025 |  | Implemented
| Shell Sprite | The sprite for the shell the player can throw, which breaks on impact | Nov 14th 2025 | Scrapped
| Key Sprite | The sprite for the key that unlocks doors | Nov 14th 2025 |  | Implemented
| Wood Texture | The texture for wood flooring | Dec 8th 2025 |  | Implemented
| Wood Door Texture | The texture for the wood door which the player unlocks with a key | Dec 8th 2025 |  | Implemented
| Level 2 Sink Hole Untouched | The sprite for the level 2 sink hole before the player touches it | Dec 8th 2025 |  | Implemented
| Level 2 Sink Hole | The sprite for the level 2 sink hole after the player touches it | Dec 8th 2025 |  | Implemented
| Level 3 Sink Hole Untouched | The sprite for the level 3 sink hole before the player touches it | Dec 8th 2025 |  | Implemented